## Summary
`
87 success criteria, classified by the checklist’s Validation Approach. LOE = net-new engineering beyond partner-provided automated checks. Effort in dev-days (blended senior eng); ≈ weeks = midpoint ÷ 5.
KEY FINDING: with the partner covering automated Level A/AA, the net-new gap is almost entirely AGENTIC (AI) + HUMAN-IN-THE-LOOP — not more automated checks. Adjust the “Coverage Source” column against the partner’s real SC list.
A · Net-new build by phase (Required A/AA = Phases 1–2)
Phase | Criteria | LOE low (d) | LOE high (d) | ≈ weeks
Phase 1 · Agentic (Req. A/AA)
Phase 2 · HITL (Req. A/AA)
Phase 3 · Optional / AAA
B · One-time + conditional workstreams
Work item | Criteria | LOE low (d) | LOE high (d) | ≈ weeks
Phase 0 · coverage audit + check contract + golden corpus | — | 5 | 8
HITL platform hardening (queue, evidence, sign-off) | — | 15 | 25
Conditional · document-format automated parity (if partner is web-only)
TOTAL → Required A/AA conformance (Phases 1–2 + Phase 0 + platform)
TOTAL → incl. AAA / Optional (Phase 3)
C · Coverage today
Coverage source | Criteria
Shipped (demo)
Partner baseline
MDK net-new
All success criteria

## Coverage Matrix
SC | Success Criterion | Level | Added In | Legal | Principle | Validation Approach | Coverage Source | Build Tier | Phase | LOE low (d) | LOE high (d) | Requirement | How to Test | Notes
1.1.1 | Non-text Content | A | 2.0 | Required | Perceivable | Automated + Agentic | Shipped (demo) | Tier 2 · Agentic AI | — |  |  | All non-text content (images, icons, charts, controls) has a text alternative serving the equivalent purpose; decorative images are marked as such. | Check alt text; verify with a screen reader (NVDA/VoiceOver); confirm decorative images use null alt / aria-hidden.
1.2.1 | Audio-only & Video-only (Prerecorded) | A | 2.0 | Required | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Provide a transcript for prerecorded audio-only and a transcript or audio track for prerecorded video-only. | Manual media review; confirm transcript/description is present.
1.2.2 | Captions (Prerecorded) | A | 2.0 | Required | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Synchronized captions for all prerecorded audio in video. | Play media; verify accurate, synchronized captions.
1.2.3 | Audio Description or Media Alternative (Prerecorded) | A | 2.0 | Required | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Audio description or full text alternative for prerecorded video. | Manual review for an audio-description track or transcript.
1.2.4 | Captions (Live) | AA | 2.0 | Required | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Real-time captions for live audio content. | Verify live captioning on streamed/live media.
1.2.5 | Audio Description (Prerecorded) | AA | 2.0 | Required | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Audio description provided for all prerecorded video. | Confirm a described audio track exists.
1.2.6 | Sign Language (Prerecorded) | AAA | 2.0 | Optional | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Sign-language interpretation for prerecorded audio. | Manual review.
1.2.7 | Extended Audio Description (Prerecorded) | AAA | 2.0 | Optional | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Extended audio description where pauses in dialogue are insufficient. | Manual review.
1.2.8 | Media Alternative (Prerecorded) | AAA | 2.0 | Optional | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Full text alternative for prerecorded synchronized media. | Confirm a complete transcript.
1.2.9 | Audio-only (Live) | AAA | 2.0 | Optional | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Text alternative for live audio-only content. | Manual review.
1.3.1 | Info and Relationships | A | 2.0 | Required | Perceivable | Automated + Agentic | Shipped (demo) | Tier 2 · Agentic AI | — |  |  | Structure/relationships shown visually are available programmatically (headings, lists, tables, form labels). | Inspect semantic markup/ARIA; screen-reader test; automated scan (axe).
1.3.2 | Meaningful Sequence | A | 2.0 | Required | Perceivable | Human / AT | Shipped (demo) | Tier 3 · HITL workflow | — |  |  | DOM reading/navigation order is logical and correct. | Disable CSS or use a screen reader to verify order.
1.3.3 | Sensory Characteristics | A | 2.0 | Required | Perceivable | Automated + Agentic | MDK net-new | Tier 2 · Agentic AI | Phase 1 · Agentic (Req. A/AA) | 4 | 8 | Instructions don't rely solely on shape, size, location, or sound (e.g. 'click the round button'). | Manual review of instructional text.
1.3.4 | Orientation | AA | 2.1 | Required | Perceivable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Content not locked to one orientation (portrait/landscape) unless essential. | Rotate device/viewport; confirm content adapts. | Partner provides for web; net-new only for PDF/Office formats
1.3.5 | Identify Input Purpose | AA | 2.1 | Required | Perceivable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Inputs collecting user info use appropriate autocomplete tokens. | Inspect autocomplete attributes on form fields. | Partner provides for web; net-new only for PDF/Office formats
1.3.6 | Identify Purpose | AAA | 2.1 | Optional | Perceivable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | Purpose of UI components, icons, and regions is programmatically determinable. | Inspect ARIA/landmark markup.
1.4.1 | Use of Color | A | 2.0 | Required | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Color is not the only means of conveying information (errors, links, states). | Manual review; grayscale check.
1.4.2 | Audio Control | A | 2.0 | Required | Perceivable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Auto-playing audio over 3s can be paused/stopped or volume controlled. | Verify a pause/stop control on autoplay audio. | Partner provides for web; net-new only for PDF/Office formats
1.4.3 | Contrast (Minimum) | AA | 2.0 | Required | Perceivable | Automated | Shipped (demo) | Tier 1 · Deterministic | — |  |  | Text contrast >= 4.5:1 (>= 3:1 for large text: 18pt, or 14pt bold). | Use a contrast analyzer on text/background pairs.
1.4.4 | Resize Text | AA | 2.0 | Required | Perceivable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Text resizable to 200% without loss of content or function. | Zoom browser to 200%; check for clipping/overlap. | Partner provides for web; net-new only for PDF/Office formats
1.4.5 | Images of Text | AA | 2.0 | Required | Perceivable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Use real text rather than images of text (except logos/essential cases). | Identify text rendered as images. | Partner provides for web; net-new only for PDF/Office formats
1.4.6 | Contrast (Enhanced) | AAA | 2.0 | Optional | Perceivable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | Text contrast >= 7:1 (>= 4.5:1 for large text). | Contrast analyzer.
1.4.7 | Low or No Background Audio | AAA | 2.0 | Optional | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Background audio behind speech is low/absent or can be turned off. | Manual review.
1.4.8 | Visual Presentation | AAA | 2.0 | Optional | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | User control over text blocks: colors, width <= 80 chars, spacing, no justification. | Manual review / user-setting test.
1.4.9 | Images of Text (No Exception) | AAA | 2.0 | Optional | Perceivable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | No images of text except where essential (e.g. logos). | Manual review.
1.4.10 | Reflow | AA | 2.1 | Required | Perceivable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Content reflows to 320 CSS px wide without 2-D scrolling (1280px at 400% zoom). | Zoom to 400% / 320px viewport; check for horizontal scroll. | Partner provides for web; net-new only for PDF/Office formats
1.4.11 | Non-text Contrast | AA | 2.1 | Required | Perceivable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | UI components and graphics have >= 3:1 contrast against adjacent colors. | Contrast analyzer on buttons, borders, icons, focus rings. | Partner provides for web; net-new only for PDF/Office formats
1.4.12 | Text Spacing | AA | 2.1 | Required | Perceivable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | No loss of content when user overrides line/letter/word/paragraph spacing. | Apply text-spacing bookmarklet; check for clipping. | Partner provides for web; net-new only for PDF/Office formats
1.4.13 | Content on Hover or Focus | AA | 2.1 | Required | Perceivable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Hover/focus content (tooltips, popovers) is dismissible, hoverable, and persistent. | Test tooltips/menus with both keyboard and pointer.
2.1.1 | Keyboard | A | 2.0 | Required | Operable | Human / AT | Shipped (demo) | Tier 3 · HITL workflow | — |  |  | All functionality is operable via keyboard. | Tab/arrow through all controls with no mouse.
2.1.2 | No Keyboard Trap | A | 2.0 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Keyboard focus can always move away from a component. | Tab into and out of every widget/modal.
2.1.3 | Keyboard (No Exception) | AAA | 2.0 | Optional | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | All functionality keyboard-operable with no timing exceptions. | Keyboard-only test.
2.1.4 | Character Key Shortcuts | A | 2.1 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Single-character shortcuts can be turned off, remapped, or active only on focus. | Test single-key shortcuts; check settings.
2.2.1 | Timing Adjustable | A | 2.0 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Time limits can be turned off, adjusted, or extended. | Identify timeouts; verify controls.
2.2.2 | Pause, Stop, Hide | A | 2.0 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Moving/blinking/auto-updating content can be paused, stopped, or hidden. | Test carousels, animations, auto-refresh.
2.2.3 | No Timing | AAA | 2.0 | Optional | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | No time limits except for real-time events. | Manual review.
2.2.4 | Interruptions | AAA | 2.0 | Optional | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Interruptions can be postponed or suppressed by the user. | Manual review.
2.2.5 | Re-authenticating | AAA | 2.0 | Optional | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | After session expiry, data is preserved on re-authentication. | Test session timeout then resume.
2.2.6 | Timeouts | AAA | 2.1 | Optional | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Users are warned of potential data loss from inactivity timeout. | Check for timeout warnings.
2.3.1 | Three Flashes or Below Threshold | A | 2.0 | Required | Operable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Nothing flashes more than 3 times per second (or stays below threshold). | Review animations/video for flashing. | Partner provides for web; net-new only for PDF/Office formats
2.3.2 | Three Flashes | AAA | 2.0 | Optional | Operable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | No content flashes more than 3 times per second. | Manual review.
2.3.3 | Animation from Interactions | AAA | 2.1 | Optional | Operable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | Motion animation from interactions can be disabled (prefers-reduced-motion). | Test reduced-motion setting.
2.4.1 | Bypass Blocks | A | 2.0 | Required | Operable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | A skip link or mechanism bypasses repeated blocks of content. | Tab from top; verify skip link / landmarks. | Partner provides for web; net-new only for PDF/Office formats
2.4.2 | Page Titled | A | 2.0 | Required | Operable | Automated | Shipped (demo) | Tier 1 · Deterministic | — |  |  | Pages have descriptive, unique titles. | Inspect the <title> element.
2.4.3 | Focus Order | A | 2.0 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Focus order preserves meaning and operability. | Tab through; verify logical order.
2.4.4 | Link Purpose (In Context) | A | 2.0 | Required | Operable | Automated + Agentic | Shipped (demo) | Tier 2 · Agentic AI | — |  |  | Link purpose is clear from text or surrounding context. | Review link text ('click here' fails).
2.4.5 | Multiple Ways | AA | 2.0 | Required | Operable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | More than one way to locate a page (nav, search, sitemap). | Confirm at least two navigation methods. | Partner provides for web; net-new only for PDF/Office formats
2.4.6 | Headings and Labels | AA | 2.0 | Required | Operable | Automated + Agentic | MDK net-new | Tier 2 · Agentic AI | Phase 1 · Agentic (Req. A/AA) | 4 | 8 | Headings and labels are descriptive. | Review heading/label text.
2.4.7 | Focus Visible | AA | 2.0 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Keyboard focus indicator is visible. | Tab through; confirm a visible focus ring.
2.4.8 | Location | AAA | 2.0 | Optional | Operable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | User's location within a set of pages is available (breadcrumbs). | Check breadcrumbs / nav state.
2.4.9 | Link Purpose (Link Only) | AAA | 2.0 | Optional | Operable | Automated + Agentic | MDK net-new | Tier 2 · Agentic AI | Phase 3 · Optional / AAA | 4 | 8 | Link purpose is clear from the link text alone. | Review link text in isolation.
2.4.10 | Section Headings | AAA | 2.0 | Optional | Operable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | Section headings organize content. | Review heading structure.
2.4.11 | Focus Not Obscured (Minimum) | AA | 2.2 | Recommended | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Focused component is not entirely hidden by author content (sticky headers, cookie banners). | Tab through; verify focused element is not fully covered.
2.4.12 | Focus Not Obscured (Enhanced) | AAA | 2.2 | Optional | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Focused component is not even partially hidden. | Keyboard test.
2.4.13 | Focus Appearance | AAA | 2.2 | Optional | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Focus indicator meets minimum size and contrast requirements. | Measure focus-indicator area and contrast.
2.5.1 | Pointer Gestures | A | 2.1 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Multipoint/path-based gestures have a single-pointer alternative. | Test pinch/swipe features for a tap alternative.
2.5.2 | Pointer Cancellation | A | 2.1 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Down-event doesn't trigger action; action can be aborted/undone (fires on up-event). | Press, drag off target, release to cancel.
2.5.3 | Label in Name | A | 2.1 | Required | Operable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Accessible name contains the visible label text. | Compare visible label vs accessible name; voice-control test. | Partner provides for web; net-new only for PDF/Office formats
2.5.4 | Motion Actuation | A | 2.1 | Required | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Motion-triggered functions have a UI alternative and can be disabled. | Test shake/tilt features for an alternative.
2.5.5 | Target Size (Enhanced) | AAA | 2.1 | Optional | Operable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | Touch targets are at least 44x44 CSS px. | Measure target sizes.
2.5.6 | Concurrent Input Mechanisms | AAA | 2.1 | Optional | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Do not restrict input modalities (touch + keyboard + mouse). | Test switching input methods.
2.5.7 | Dragging Movements | AA | 2.2 | Recommended | Operable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Dragging actions have a single-pointer, non-drag alternative. | Test sliders / drag-drop for a click alternative.
2.5.8 | Target Size (Minimum) | AA | 2.2 | Recommended | Operable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Pointer targets are at least 24x24 CSS px (or adequate spacing / exceptions). | Measure interactive target sizes and spacing. | Partner provides for web; net-new only for PDF/Office formats
3.1.1 | Language of Page | A | 2.0 | Required | Understandable | Automated | Shipped (demo) | Tier 1 · Deterministic | — |  |  | Default human language set programmatically (lang attribute). | Inspect <html lang>.
3.1.2 | Language of Parts | AA | 2.0 | Required | Understandable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Language of passages/phrases set where it differs from the page default. | Inspect lang on foreign-language content. | Partner provides for web; net-new only for PDF/Office formats
3.1.3 | Unusual Words | AAA | 2.0 | Optional | Understandable | Automated + Agentic | MDK net-new | Tier 2 · Agentic AI | Phase 3 · Optional / AAA | 4 | 8 | Definitions provided for jargon and idioms. | Manual review.
3.1.4 | Abbreviations | AAA | 2.0 | Optional | Understandable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | Expanded form of abbreviations available. | Manual review.
3.1.5 | Reading Level | AAA | 2.0 | Optional | Understandable | Automated | MDK net-new | Tier 1 · Deterministic | Phase 3 · Optional / AAA | 1 | 3 | Supplemental content where text exceeds lower-secondary reading level. | Readability assessment.
3.1.6 | Pronunciation | AAA | 2.0 | Optional | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Pronunciation provided where meaning is otherwise ambiguous. | Manual review.
3.2.1 | On Focus | A | 2.0 | Required | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Receiving focus does not trigger a change of context. | Tab through; confirm no unexpected changes.
3.2.2 | On Input | A | 2.0 | Required | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Changing a setting does not auto-trigger a context change without warning. | Test form inputs and selects.
3.2.3 | Consistent Navigation | AA | 2.0 | Required | Understandable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Navigation repeated across pages appears in a consistent order. | Compare navigation across pages. | Partner provides for web; net-new only for PDF/Office formats
3.2.4 | Consistent Identification | AA | 2.0 | Required | Understandable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Components with the same function are identified consistently. | Compare icons/labels across pages. | Partner provides for web; net-new only for PDF/Office formats
3.2.5 | Change on Request | AAA | 2.0 | Optional | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Context changes only on user request. | Manual review.
3.2.6 | Consistent Help | A | 2.2 | Recommended | Understandable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Help mechanisms (contact, chat, FAQ) appear in a consistent relative order across pages. | Verify help-location consistency. | Partner provides for web; net-new only for PDF/Office formats
3.3.1 | Error Identification | A | 2.0 | Required | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Input errors are identified and described in text. | Submit an invalid form; check error messaging.
3.3.2 | Labels or Instructions | A | 2.0 | Required | Understandable | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | Labels/instructions are provided for user input. | Review form fields for labels and hints. | Partner provides for web; net-new only for PDF/Office formats
3.3.3 | Error Suggestion | AA | 2.0 | Required | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Correction suggestions are provided when known. | Trigger errors; check for suggestions.
3.3.4 | Error Prevention (Legal, Financial, Data) | AA | 2.0 | Required | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Submissions are reversible, checked, or confirmed for legal/financial/data actions. | Test checkout/submit for a confirm/review step.
3.3.5 | Help | AAA | 2.0 | Optional | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Context-sensitive help is available. | Manual review.
3.3.6 | Error Prevention (All) | AAA | 2.0 | Optional | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | All submissions are reversible, checked, or confirmed. | Manual review.
3.3.7 | Redundant Entry | A | 2.2 | Recommended | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | Previously entered info is auto-populated or selectable, not re-entered. | Test multi-step forms.
3.3.8 | Accessible Authentication (Minimum) | AA | 2.2 | Recommended | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | No cognitive-function test (memorize/transcribe) without an alternative; allow paste and password managers. | Review login/auth flow; test password-manager paste.
3.3.9 | Accessible Authentication (Enhanced) | AAA | 2.2 | Optional | Understandable | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 3 · Optional / AAA | 1 | 2 | No cognitive-function test at all (no object-recognition exception). | Review auth flow.
4.1.1 | Parsing | A | 2.1 (removed in 2.2) | Required | Robust | Automated | Partner baseline | Tier 1 · Deterministic | — |  |  | OBSOLETE in WCAG 2.2 - always passes. Historically: well-formed markup, no duplicate IDs. | Mark N/A for a 2.2-scoped audit; was an HTML-validity check under 2.0/2.1. | Partner provides for web; net-new only for PDF/Office formats
4.1.2 | Name, Role, Value | A | 2.0 | Required | Robust | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | UI components expose correct name, role, state, and value to assistive tech (critical for custom/ARIA widgets). | Screen-reader test; inspect ARIA; automated scan.
4.1.3 | Status Messages | AA | 2.1 | Required | Robust | Human / AT | MDK net-new | Tier 3 · HITL workflow | Phase 2 · HITL (Req. A/AA) | 1 | 2 | Status messages are conveyed to assistive tech without a focus change (aria-live). | Trigger dynamic updates; verify announcement.

## By Tier
Build tier | Net-new | LOE low (d) | LOE high (d) | Meaning
Tier 1 · Deterministic |  |  |  | Rule on parsed document model; ×4 formats
Tier 2 · Agentic AI |  |  |  | LLM evaluator + golden evals + confidence + HITL escalation
Tier 3 · HITL workflow |  |  |  | Detector + routed human review + evidence capture